## Status R3.1
SVT-status Systest3 | [12 empty] | UAT - status
Testcase | Market trial | Imb.settl./Recon. | Mand/ Opt | Req. to M7 | Internal Status |  | External Status |  | Elhub defect | External comment | Internal comment | Navn | UAT Test case | Status UAT R3.1 | Sanity check IDC ST3 | Priority | Expected deploy date in QA (SVT 3 days later)
BRS-NO-101 Confirm | Yes | No | M | Yes | 2017-12-14 | Pass | 2017-11-21 | Pass |  |  |  | Kim | UAT-188,UAT-189,UAT-194 | Pass | Pass |  |  | Fail
BRS-NO-101 Reject | Yes | No | M | Yes | 2017-10-03 | Pass | 2017-11-07 | Pass |  |  |  | Truls | UAT-1021 | Pass | Pass |  |  | Partial/Wait
BRS-NO-101 Cancel | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-11-03 | Pass |  |  |  | Truls | UAT-934 | Pass |  |  |  | Pass
BRS-NO-102 Confirm | Yes | No | M | Yes | 2017-12-14 | Pass | 2017-10-17 | Pass |  |  |  | Kim | UAT-202,UAT-203,UAT-7324 | Pass |  |  |  | Not tested
BRS-NO-102 Reject | Yes | No | M | Yes | 2017-10-03 | Pass | 2017-10-17 | Pass |  |  |  | Truls | UAT-7323 | Pass
BRS-NO-102 Cancel | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-10-10 | Pass |  |  |  | Truls | UAT-811 | Pass |  |  |  | In client verification
BRS-NO-103 Profiled | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-11-09 | Pass |  |  |  | Kim | UAT-210 | Pass | Pass
BRS-NO-104 | Yes | No | M | Yes | 2017-12-14 | Pass | 2017-12-11 | Pass |  |  |  | Kim | UAT-7325 | Pass
BRS-NO-104 Neg | No | No | O | Yes | 2017-10-02 | Pass | 2017-10-06 | Pass |  |  |  | Truls | UAT-6579 | Pass
BRS-NO-111-1 | Yes | No | M | Yes | 2017-12-14 | Pass | 2017-11-21 | Pass |  |  |  | Kim | UAT-6413 | Pass | Pass
BRS-NO-111-2 | No | No | M | Yes | 2017-12-14 | Pass | 2017-11-21 | Pass |  |  |  | Kim | UAT-1035 | Pass
BRS-NO-111-3 | No | No | M | Yes | 2017-10-02 | Pass | 2017-11-21 | Pass |  |  |  | Kim | UAT-1067 | Pass
BRS-NO-111-4 | Yes | No | M | Yes | 2017-12-14 | Pass | 2017-11-21 | Pass |  |  |  | Kim | UAT-814 | Pass
BRS-NO-121 | Yes | No | M | Yes | 2017-10-02 | Pass | 2017-10-03 | Pass |  |  |  | Kim | UAT-1006 | Pass
BRS-NO-121 Neg | No | No | O | Yes | 2017-09-28 | Pass | 2017-10-03 | Pass |  |  |  | Truls | UAT-775 | Pass
BRS-NO-122 | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-10-03 | Pass |  |  |  | Kim | UAT-218 | Pass | Pass
BRS-NO-122 Neg | No | No | O | Yes | 2017-10-02 | Pass | 2017-11-21 | Pass |  |  |  | Truls | UAT-219 | Pass
BRS-NO-123 | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-10-03 | Pass |  |  |  | Kim | UAT-234 | Pass | Pass
BRS-NO-132 | No | No | M | Yes | 2017-10-02 | Pass | 2017-10-04 | Pass |  |  |  | Kim | UAT-221 | Pass
BRS-NO-133 | No | No | M | Yes | 2017-10-02 | Pass | 2017-12-07 | Pass |  |  |  | Kim | UAT-1075 | Pass
BRS-NO-201 | Yes | No | M | Yes | 2018-12-12 | Pass | 2017-10-03 | Pass |  |  |  | Kim | UAT-717,UAT-955,UAT-241 | Pass
BRS-NO-201 Cancel | Yes | No | M | Yes | 2017-10-13 | Pass | 2017-10-13 | Pass |  |  |  | Truls | UAT-935 | Pass |  | 1
BRS-NO-202 | Yes | No | M | Yes | 2018-12-12 | Pass | 2017-10-21 | Pass |  |  |  | Ola | UAT-900,UAT-888,UAT-834 | Pass
BRS-NO-202 Cancel | Yes | No | M | Yes | 2017-10-13 | Pass | 2017-10-13 | Pass |  |  |  | Ola | UAT-818 | Pass |  | 1
BRS-NO-211 | No | No | M | Yes | 2017-10-02 | Pass | 2017-10-27 | Pass |  |  |  | Kim | UAT-731 | Pass
BRS-NO-211 Cancel | No | No | M | Yes | 2017-10-03 | Pass | 2017-10-25 | Pass |  |  |  | Kim | UAT-951 | Pass
BRS-NO-211 Correct | No | No | M | Yes | 2017-12-19 | Pass | 2017-12-05 | Pass |  |  |  |  | UAT-1045 | Pass |  | 1
BRS-NO-212 | No | No | M | Yes | 2017-10-03 | Pass | 2017-10-04 | Pass |  |  |  | Christine | UAT-6435 | Pass |  | 1 | 2017-10-09
BRS-NO-213 | No | No | M | Yes | 2017-10-03 | Pass | 2017-10-04 | Pass |  |  |  | Truls | UAT-756 | Pass
BRS-NO-221-1 | No | No | M | Yes |  | Pass |  | Pass |  |  |  | Kim | UAT-760 | Pass
BRS-NO-221-2 | No | No | M | Yes |  | Pass | 2017-12-14 | Pass |  |  |  |  | UAT-791 | Pass
BRS-NO-222 | No | No | M | Yes | 2017-11-09 | Pass | 2017-10-25 | Pass |  |  |  | Kim | UAT-1029 | Pass | Pass
BRS-NO-223 | No | No | M | Yes | 2017-10-03 | Pass | 2017-12-04 | Pass |  |  |  | Truls | UAT-1053 | Pass
BRS-NO-224 | No | No | M | Yes | 2017-10-04 | Pass | 2017-11-21 | Pass |  |  |  |  | UAT-891 | Pass
BRS-NO-301 | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-10-05 | Pass |  |  |  | Kim | UAT-684 | Pass | Pass
BRS-NO-301 Neg | No | No | O | Yes | 2017-10-04 | Pass | 2017-11-21 | Pass |  |  |  |  | UAT-1003 | Pass
BRS-NO-302 | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-10-05 | Pass |  |  |  | Kim | UAT-904 | Pass | Pass | 1
BRS-NO-302 Neg | No | No | O | Yes |  | Pass | 2017-10-06 | Pass |  |  |  |  | UAT-995 | Pass
BRS-NO-303 | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-10-04 | Pass |  |  |  | Kim | UAT-6892 | Pass | Pass
BRS-NO-303 Neg | No | No | O | Yes | 2017-10-04 | Pass | 2017-10-06 | Pass |  |  |  |  | UAT-6930 | Pass
BRS-NO-305-1 | No | No | M | No | 2018-03-22 | Pass | 2018-03-23 | Pass |  |  |  | Erik | UAT-87 | Pass |  | 2
BRS-NO-305-2 | No | No | M | Yes | 2018-01-24 | Pass | 2018-01-24 | Pass |  |  |  | Erik | UAT-73,UAT-54 | Pass
BRS-NO-305-3 | No | No | M | No | 2018-03-22 |  |  |  | ED-18858 | RequestStartOfSupply to new BSOLR missing |  | Erik | UAT-98 | Pass |  | 2
BRS-NO-306 | Yes | No | M | Yes | 2017-09-27 | Pass | 2017-10-06 | Pass |  |  |  | Kim | UAT-1073 | Pass
BRS-NO-311 Meter | Yes | No | M | Yes | 2017-09-28 | Pass | 2017-10-04 | Pass |  |  |  | Anita | UAT-6165 | Pass | Pass
BRS-NO-311 EAC | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-10-04 | Pass |  |  |  | Kim | UAT-6170 | Pass | Pass
BRS-NO-312 | Yes | Yes | M | Yes | 2017-11-09 | Pass | 2017-10-05 | Pass |  |  |  | Kim | UAT-251 | Pass | Pass | 1
BRS-NO-313 | Yes | Yes | M | Yes | 2017-11-09 | Pass | 2017-10-05 | Pass |  |  |  | Anita | UAT-7321 | Pass | Pass | 1
BRS-NO-314-1 | Yes | Yes | M | Yes | 2018-01-30 | Pass | 2018-01-30 | Pass |  |  |  | Alf | UAT-353 | Pass |  | 1
BRS-NO-314-2 | No | Yes | M | No | 2018-02-21 | Pass | 2018-02-21 | Pass |  |  |  | Alf | UAT-372 | Pass |  | 1
BRS-NO-314-3 | No | Yes | M | Yes | 2017-11-09 | Pass |  | Pass |  |  |  | Alf | UAT-368 | Pass |  | 1
BRS-NO-315 | Yes | Yes | M | Yes | 2017-11-10 | Pass | 2017-12-07 | Pass | ED-17237 | Defect only in Exatest2 |  | Anita | UAT-301 | Pass |  | 1
BRS-NO-315 Neg | Yes | No | O | Yes | 2017-10-25 | Pass | 2017-11-07 | Pass |  |  |  | Anita | UAT-302 | Pass
BRS-NO-317 | No | Yes | M | Yes | 2017-10-03 | Pass | 2017-10-04 | Pass |  |  |  | Kim | UAT-265 | Pass
BRS-NO-321 | No | Yes | M | Yes | 2018-12-19 | Pass | 2017-10-16 | Pass |  |  |  | Alf | UAT-354 | Pass |  | 2
BRS-NO-322 | No | Yes | M | Yes | 2017-11-09 | Pass | 2017-10-16 | Pass |  |  |  | Alf | UAT-358 | Pass | Pass | 2 | 2017-10-02
BRS-NO-324-1 | Yes | Yes | M | No | 2018-03-02 | Pass | 2018-01-04 | Pass |  |  |  | Alf | UAT-350 | Pass |  | 1
BRS-NO-324-2 | No | Yes | O | Yes | 2018-12-19 | Pass | 2018-01-04 | Pass |  |  |  | Alf | UAT-367 | Pass
BRS-NO-332 | No | Yes | M | Yes | 2017-10-05 | Pass | 2017-12-08 | Pass |  |  |  | Alf | UAT-259 | Pass |  | 1
BRS-NO-402 | Yes | No | M | Yes | 2017-10-02 | Pass | 2017-10-04 | Pass |  |  |  | Kim | UAT-937 | Pass
BRS-NO-402 Neg | No | No | O | Yes | 2017-10-04 | Pass | 2017-11-21 | Pass |  |  |  |  | UAT-205 | Pass
BRS-NO-502-1 | No | Yes | M | Yes | 2018-01-20 | Pass | 2017-10-16 | Pass |  |  |  | Alf | UAT-330 | Pass |  | 2
BRS-NO-502-2 | No | Yes | M | Yes | 2018-01-20 | Pass | 2017-10-16 | Pass |  |  |  | Alf | UAT-330 | Pass |  | 2
BRS-NO-502-3 | No | Yes | M | Yes | 2018-01-21 | Pass | 2017-10-16 | Pass |  |  |  | Alf | UAT-330 | Pass |  | 2
BRS-NO-503-1 | No | Yes | M | No | 2018-02-21 | Pass | 2018-02-21 | Pass |  |  |  | Alf | UAT-339 |  |  | 3 | 2017-10-07
BRS-NO-503-2 | No | Yes | M | No | 2018-02-21 | Pass | 2018-02-21 | Pass |  |  |  | Alf | UAT-339 |  |  | 3 | 2017-10-07
BRS-NO-601-1 | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-10-05 | Pass |  |  |  | Ola | UAT-1226,UAT-1229 | Pass | Pass
BRS-NO-601-2 | Yes | No | M | Yes | 2017-10-03 | Pass | [5 empty] | Ola | UAT-1228,UAT-1247 | Pass
BRS-NO-611 with ID | Yes | No | M | Yes | 2017-10-02 | Pass | 2017-10-03 | Pass |  |  |  | Kim | UAT-1331 | Pass |  | 1
BRS-NO-611 with MPID | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-10-03 | Pass |  |  |  | Kim | UAT-1329 | Pass | Pass
BRS-NO-622-1 | Yes | No | M | Yes | 2017-10-03 | Pass | 2018-03-12 | Pass |  |  | CRT: ED-13733 C-defect | Kim | UAT-6134,UAT-6136 | Pass | Pass
BRS-NO-622-2 | Yes | No | M | Yes | 2017-10-03 | Pass |  |  |  |  | Krever Plug-in | Kim | UAT-6145 | Pass
BRS-NO-622-3 | No | No | M | Yes | 2017-10-03 | Pass |  |  |  |  | Krever Plug-in |  | UAT-6146 | Pass
BRS-NO-602 | Yes | No | M | Yes | 2017-11-09 | Pass | 2017-10-05 | Pass |  |  |  | Ola | UAT-1286,UAT-1301 | Pass | Pass

## Open defects
Defect no | Registered | Description | Status in UAT | Updated | Estimated ready for retesting in SVT
ED-17237 | 2018-01-31 | Market parties does not receive response for BRS-NO-315 | Client verification |  | 2018-03-23
ED-18858 | 2018-03-22 | ESB_PRO_29 ChangeBSOLRForMGAProcess - RequestStartOfSupply message to new BSOLR missing | Analysis in progress

## Closed defects
Defect no | Registered | Description | Status | Estimated ready for retesting in SVT
ED-9759 | 2017-05-08 | UAT ¦ Results from imbalance settlement are not created as outgoing messages. BRS-NO-321 BRS-NO-502 | Closed
ED-11848 | 2017-07-26 | TriggerSendReconciliationResult is not working. BRS-NO-503 | Closed
ED-12296 | 2017-07-05 | ESB_PRO_30 MoveBalanceSupplierPortfoliProcess - Bulk report has incorrect content | Closed
ED-12404 | 2017-09-22 | BRS-NO-302/BRS-NO-306 Date validation is wrong | Closed
ED-12585 | 2017-10-09 | BRS-NO-332 - No response to DDM or DDQ | Analysis in progress
ED-12613 | 2017-08-23 | Metering values messages are not always processed | Closed
ED-12925 | 2017-09-04 | Functional Regression ¦ ExaTest1 ¦ BRS-NO-302 ¦ Instances coming in PRO 1 after a long time and going into Recovery | Closed | 06.10.2017. Was affecting 302 and 306
ED-13034 | 2017-10-05 | No BRS-NO-314 messages received in ST3 for profiled volumes. | Closed
ED-13081 | 2017-09-11 | Elhub Web Portal - Do not see Meter read | Reopened | 2017-10-17 08:30
ED-13134 | 2017-09-12 | QA ¦ ESB-PRO-21 failing in CalculateImbalanceSettlementResult operation | Closed
ED-13172 | 2017-09-13 | BRS-NO-302 - Currenct Balance Supplier doesn't receive NotifyMeteringPointCharacteristics | Closed
ED-13174 | 2017-09-13 | SVT verification - Missing messages after BRS-NO-102->BRS-NO-302->BRS-NO-306->BRS-NO-111 | Closed
ED-13194 | 2017-09-13 | Running MTMCheckMissingPeriodVolume-job fails due to expired password | Closed
ED-13197 | 2017-09-13 | BRS-NO-315 went into recovery | Closed
ED-13201 | 2017-09-13 | Missing interval for metering point not present in outgoing BRS-NO-314 | Closed
ED-13070 | 2017-09-11 | Elhub Web portal - metering values missing | Closed | 2017-10-25
ED-13220 | 2017-09-14 | BRS-NO-211 - Correction of move out failed with EH018 | Closed | 2017-10-06 08:30
ED-13223 | 2017-09-14 | BRS-NO-315 - aborted - no response | Closed
ED-13225 | 2017-09-14 | ESB_PRO_35 StructureDataUpdateBulkProcess - Move Accounting points - Failed | Closed
ED-13226 | 2017-09-14 | BRS-NO-324 ¦ Ends up in DLQ | Closed
ED-13234 | 2017-09-14 | BRS-NO-221 - Rollback completed successfuly - Missing NotifyEndOfSupply (Rollback) and NotifyStartOfSupply | Closed
ED-13245 | 2017-09-15 | ESB_PRO_30 Move BalanceSupplierPortfolio - Failed | Closed
ED-13267 | 2017-09-15 | BRS-NO-123 NotifyStartOfSupply to BSLR (and to GAP) has too many measurement definitions | Closed
ED-13294 | 2017-09-18 | Does not show current balance supply contract after cancellation deadline of BRS-NO-202 in Elhub Web portal | Closed
ED-13299 | 2017-09-18 | BRS-NO-221 - missing messages after completed successfull | Closed
ED-13300 | 2017-09-18 | 2.1.0 - Balance Supply contract has new start date after rollback with BRS-NO-221 | Closed
ED-13345 | 2017-09-19 | BRS-NO-315: No response when requesting/polling hourly values | Closed
ED-13578 | 2017-09-28 | BRS-NO-305 StructureDataUpdateBulkProcess - Move Accounting points - Error in sub-process | Closed
ED-13710 | 2017-09-30 | Usage date time start and end in Imbalance Settlement Query Services misaligned with Oslo time | Closed
ED-13711 | 2017-09-30 | UAT ¦ BRS-NO-315 is not sending PPC and FPC metering values | Closed
ED-13733 | 2017-10-05 | Not able to use dropdown menu to see who the user is representing in Elhub Web Plugin | Closed
ED-13746 | 2017-10-03 | BRS-NO-101/BRS-NO-102: Flow state = suspended in SOA | Closed | 2017-10-06 08:30
ED-13818 | 2017-10-05 | Missing 502 and 321, NBS message on D+3 and D+4 | Closed
ED-13824 | 2017-10-05 | Loss is missing in the 321 message | Closed
ED-13828 | 2017-10-05 | SE24 in 321 includes pumped consumption | Closed
ED-13843 | 2017-10-05 | System Vendor does not receive ConfirmEndOfSupply/E02 for BRS-201 Cancel and BRS-202 Cancel | Client verification | 2017-10-13
ED-13876 | 2017-10-06 | BRS-NO-211 - Correction of move out failed with EH003 | Closed
ED-13881 | 2017-10-07 | BRS-NO-211 - Process went into recovery on Cancellation Deadline | Rejected
ED-13885 | 2017-10-07 | BRS-NO-211 - Correction - NotifyEndOfSupply and ConfirmEndOfSupply is missing | Closed | 2017-10-26
ED-13926 | 2017-10-09 | BRS-NO-321 ¦ SE14 is not grouped by usage_time_id | Closed
ED-13934 | 2017-10-09 | Elhub does not verify End User ID in BRS-NO-611 | Closed
ED-14011 | 2017-10-16 | BRS 324 returns totals instead of sums per market party | Closed
ED-14012 | 2017-10-16 | BRS 324: Pumped consumption included where it should not | Closed
ED-14013 | 2017-10-16 | SE15 and SE16 are missing towards DDQ in 324 | Closed
ED-14540 | 2017-10-30 | System vendor CGI does not get NotifyValidatedDataForBillingEnergy to DDQ for BRS-NO-104 | Closed
ED-14554 | 2017-10-30 | BRS-NO-306 - NotifyMeteringPointCharacteristics to current DDQ is missing - has future DDQ | Closed
ED-14558 | 2017-10-30 | Move Balance Supplier portfolio to new Balance Supplier and send messages to the balance suppliers BRS-NO-305 goes into Recovery | Closed
ED-14855 | 2017-11-07 | BRS-NO-502 for DDK when polling as DDM received | Closed
ED-15025 | 2017-11-10 | BRS-NO-315 is not sending FPC | Closed
ED-15844 | 2018-12-06 | ESB_PRO_35 StructureDataUpdateBulkProcess - Move accounting points - Internal error in FlexSync | Closed
ED-15982 | 2017-12-12 | BRS-NO-201 and 202 goes into recovery | Closed
ED-15983 | 2017-12-12 | Elhub Operator manually recover BRS-NO-202 -> process gets aborted | Closed
ED-16005 | 2017-12-12 | 211 Correct goes into Recovery | Closed
ED-16077 | 2018-12-06 | ESB_PRO_29 ChangeBSOLRForMGAProcess - Failed | Closed
ED-16255 | 2018-12-20 | Systest3 Web portal - Validation of XML failed in OSB | Closed
ED-16678 | 2018-01-12 | BRS-NO-315 from CGI's SLR goes into recovery | Closed
ED-16954 | 2018-01-22 | ESB_PRO_35 StructureDataUpdateBulkProcess - Move Accounting points - Message to BS and GO missing | Closed
ED-17081 | 2018-01-24 | ESB_PRO_30_MoveBalanceSupplierPortfolio - Failed with error Internal error in FlexSync occurred | Closed
ED-17206 | 2018-01-31 | BRS-NO-324 receives E0H for market party | Closed
ED-17266 | 2018-02-01 | ALT_JOB_ID not getting populated for reconciliation delivery requests on QA | Closed
ED-17660 | 2018-02-17 | ATAM messages not being received | Closed
ED-17692 | 2018-02-17 | ESB_PRO_35 StructureDataUpdateBulkProcess - Move Accounting points - Error in sub process | Closed
ED-18030 | 2018-02-23 | ESB_PRO_30_MoveBalanceSupplierPortfolio - 2 Messages to New Balance Supplier missing | Closed

## Defects_OLD (hidden)
BRS | Defect | Avhengighet andre defects | TI-ticket | Status
BRS-NO-101 Confirm | ED-13213 ED-13230 |  |  | Closed Closed
BRS-NO-102 Confirm | ED-13213 ED-13230 |  |  | Closed Closed
BRS-NO-103 Profiled | ED-13216 |  |  | Closed
BRS-NO-111-2 | ED-13174 |  |  | Test on Client Environment
BRS-NO-123 | ED-13235 |  |  | Test on Client Environment
BRS-NO-211 Correct | ED-13220 |  |  | Test
BRS-NO-221-1 | ED-13234 |  |  | Client Verification
BRS-NO-302 | ED-13172 |  |  | Analysis in progress
BRS-NO-302 Neg | ED-12404 |  |  | Client Verification
BRS-NO-305-1 | ED-12296 |  |  | Analysis in progress
BRS-NO-305-3 | ED-13225 | ED-13179 |  | Analysis in progress
BRS-NO-306 | ED-13174 |  |  | Test in Client environment
BRS-NO-314-1 | Defect utarbeides
BRS-NO-314-2 | ED-13194 |  | TI-12592 | Closed
BRS-NO-314-3 | ED-13201 |  |  | Analysis in progress
BRS-NO-315 | ED-13223 |  |  | Waiting for deployment
BRS-NO-321 | ED-9759 | ED-13134 | TI-12604 | Analysis in progress
BRS-NO-322 | ED-11378 |  |  | Test in Client environment
BRS-NO-324-1 | ED-13226 |  | TI-12682 | Waiting for deployment
BRS-NO-324-2 | ED-13226 |  | TI-12682 | Waiting for deployment
BRS-NO-502-1 | ED-9759 | ED-13134 | TI-12604 | Analysis in progress
BRS-NO-502-2 | ED-9759 | ED-13134 | TI-12604 | Analysis in progress
BRS-NO-502-3 | ED-9759 | ED-13134 | TI-12604 | Analysis in progress
BRS-NO-503-1 | ED-11848 | ANSTNT-277 |  | Blocked by eMeter Hotfix delivered 27/9
BRS-NO-503-2 | ED-11848 | ANSTNT-277 |  | Blocked by eMeter Hotfix delivered 27/9